## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority Level | Status | Resource Allocation | Budget (USD) | Actual Spend (USD) | Variance (%)
T001 | Project Planning Workshop | John Smith | 2024-03-15 | 2024-03-17 | 3 | High | Completed | 1 FTE x 3 days | 1,200.00 | 1,200.00 | 0.0%
T002 | Market Research Analysis | Sarah Lee | 2024-03-18 | 2024-04-05 | 18 | Medium | In Progress | 2 FTE x 9 days | 8,000.00 | 4,500.00 | -43.75%
T003 | UI/UX Design Finalization | Mike Chen | 2024-04-06 | 2024-04-15 | 10 | High | Pending | 3 FTE x 5 days | 15,000.00 | 0 | -
T004 | Development Sprint Phase | Team A | 2024-04-16 | 2024-05-31 | 46 | Critical | Not Started | 8 FTE x 23 days | 40,000.00 | 0 | -
T005 | QA Testing & Validation | Lisa Wang | 2024-06-01 | 2024-06-30 | 30 | High | Not Started | 4 FTE x 15 days | 20,000.00 | 0 | -