## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget (USD) | Actual Cost (USD) | Variance
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-03-15 | 2024-03-15 | 1 | High | Completed | 500 | 480 | 20
TSK-002 | Market Research Phase | John Doe | 2024-03-16 | 2024-04-15 | 30 | Medium | In Progress | 8,000.00 | 4,200.00 | +3,800.00
TSK-003 | Product Design Finalization | Lisa Chen | 2024-04-16 | 2024-05-31 | 56 | High | Pending | 12,000.00 | 0 | 12,000.00
TSK-004 | Development Phase Start | Mark Taylor | 2024-06-01 | 2024-08-31 | 90 | Critical | Planned | 25,000.00 | 0 | 25,000.00