## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget (USD) | Actual Cost (USD)
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | 1 | High | Completed | 500 | 480
T002 | Market Research Phase | Sarah Lee | 2024-04-03 | 2024-04-15 | 13 | Medium | In Progress | 8,000.00 | 5,200.00
T003 | Design Finalization | Mike Chen | 2024-04-16 | 2024-05-10 | 25 | High | Planned | 12,000.00 | 0
T004 | Development Phase | Emily Davis | 2024-05-11 | 2024-07-31 | 92 | High | Not Started | 45,000.00 | 0
T005 | Testing & Quality Assurance | David Brown | 2024-08-01 | 2024-08-31 | 31 | Medium | Planned | 7,500.00 | 0
T006 | Deployment & Launch | Lisa Wong | 2024-09-01 | 2024-09-15 | 15 | High | Not Started | 6,000.00 | 0
Total Budget: |  |  |  | 67,000.00 | Actual Spend (So Far): |  |  | 10,680.00