## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Budget Allocation ($) | Priority
T001 | Project Planning Phase | Alex Morgan | 2024-03-15 | 2024-03-25 | 10 | On Track | 5,000.00 | High
T002 | User Requirement Gathering | Jordan Lee | 2024-03-26 | 2024-04-10 | 15 | In Progress | 7,500.00 | High
T003 | UI/UX Design Finalization | Samantha Chen | 2024-04-11 | 2024-05-05 | 25 | Pending | 12,000.00 | Medium
T004 | Development Phase (Phase 1) | David Kim | 2024-05-06 | 2024-06-15 | 40 | Not Started | 35,000.00 | High
T005 | Testing & Quality Assurance | Taylor Reed | 2024-06-16 | 2024-07-10 | 35 | Planned | 18,000.00 | Medium