## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget Allocation ($) | Actual Cost ($) | Variance ($)
TSK-001 | Project Planning | John Doe | 2024-03-01 | 2024-03-15 | 15 | High | Completed | 5,000 | 4,800 | 200
TSK-002 | Requirement Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | 35 | Medium | In Progress | 8,000 | 6,200 | +1,800
TSK-003 | System Design | Alex Brown | 2024-04-11 | 2024-05-05 | 35 | High | Planned | 12,000 | 0 | -12,000
TSK-004 | Development Phase | Sam Lee | 2024-05-06 | 2024-07-15 | 70 | High | Pending | 35,000 | 0 | -35,000
Total Budget Allocation |  |  |  |  | $50,000 | $11,000 | $39,000