## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget (USD) | Actual Cost (USD)
T001 | Project Planning Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | 500 | 480
T002 | Design Phase Kickoff | Jane Smith | 2024-04-02 | 2024-04-15 | 14 | Medium | In Progress | 2,500.00 | 1,800.00
T003 | Development Sprint 1 | Alex Johnson | 2024-04-16 | 2024-05-10 | 35 | High | Not Started | 8,000.00 | 0
T004 | Quality Assurance Testing | Sarah Lee | 2024-05-11 | 2024-05-30 | 20 | Medium | Not Started | 3,200.00 | 0