## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Budget Allocation
T001 | Project Planning Meeting | John Doe | 2024-04-01 | 2024-04-01 | Completed | High | 2 | 2 | $150.00
T002 | Market Research Analysis | Sarah Lee | 2024-04-03 | 2024-04-15 | In Progress | Medium | 8 | 4.5 | $600.00
T003 | Design Prototype Review | Michael Chen | 2024-04-16 | 2024-04-25 | Pending | Low | 6 | 0 | $300.00
T004 | Client Presentation Prep | Lena Patel | 2024-05-01 | 2024-05-10 | Completed | High | 10 | 10 | $900.00