## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Budget Allocation ($) | Status | Priority
TS-001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Jane Smith | 500 | Completed | High
TS-002 | <Market Analysis Phase | 2024-04-02 | 2024-04-15 | 14 | Alex Johnson | 3,500.00 | In Progress | High
TS-003 | Product Design Finalization | 2024-04-16 | 2024-05-10 | 35 | Sara Lee | 8,000.00 | Planned | Medium
TS-004 | Development Sprint 1 | 2024-05-11 | 2024-06-15 | 45 | Mark Taylor | 15,000.00 | Scheduled | High
TS-005 | User Testing & Feedback | 2024-06-16 | 2024-07-15 | 30 | Linda Wong | 4,200.00 | Pending Approval | Medium