## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget Allocation ($) | Resource Required
T-001 | Project Kickoff Meeting | John Doe | 2024-03-15 | 2024-03-15 | 1 | High | Completed | 500 | Meeting Room, 1 HR
T-002 | Market Research Analysis | Jane Smith | 2024-03-18 | 2024-03-25 | 7 | Medium | In Progress | 1,500.00 | Research Team, 3 HRs
T-003 | Development Phase Planning | Alex Johnson | 2024-04-01 | 2024-04-15 | 15 | High | Pending | 3,000.00 | Dev Team, 15 HRs
T-004 | User Testing & Feedback | Sarah Lee | 2024-05-01 | 2024-05-10 | 10 | Medium | Not Started | 2,200.00 | QA Team, 8 HRs
T-005 | Final Deployment & Review | Mike Brown | 2024-06-01 | 2024-06-15 | 15 | High | Planned | 4,800.00 | IT Team, 25 HRs