## Worksheet
Task Scheduling Budget Template
Project Overview
Project Name | Task Planning & Resource Allocation
Project Duration | 3 Months (September – November 2024)
Primary Objective | Optimize task flow, reduce delays, and ensure team productivity.
Task Schedule & Budget Breakdown
Task | Duration (Days) | Responsible Person | Estimated Cost ($) | Status
Project Initiation & Planning | 5 | Manager A | $2,000 | On Track
Resource Allocation & Team Setup | 7 | HR Coordinator B | $3,500 | Pending Approval
Phase I Development | 20 | Team Lead C | $8,000 | In Progress
Testing & Quality Assurance | 10 | QA Engineer D | $4,500 | Planned
Final Review & Deployment | 5 | Project Manager A | $2,500 | Not Started
Total Estimated Budget
$20,000
Prepared by: Project Office ¦ Date: October 5, 2024