## Task Scheduling Budget Template
Task ID | Task Name | Description | Start Date | End Date | Responsible Person | Estimated Hours | Budget Allocation (USD) | Status
#T001 | Project Initiation | Finalize project scope and stakeholders. | 2024-03-15 | 2024-03-20 | Jane Smith | 8
#T002 | Requirements Gathering | Conduct workshops to collect user needs. | 2024-03-21 | 2024-03-31 | Marcus Lee | 16 | 800 | In Progress
#T003 | Design Phase | Create wireframes and UI mockups. | 2024-04-01 | 2024-04-15 | Sarah Kim | 32 | 1600 | Pending Approval
#T004 | Development Phase | Build frontend and backend modules. | 2024-04-16 | 2024-05-31 | David Brown | 120 | 6000 | Not Started
#T005 | Testing & QA | Conduct unit, integration, and user acceptance testing. | 2024-06-01 | 2024-06-15 | Lisa Wong | 48 | 2400 | Planned
#T006 | Deployment & Launch | Migrate to production and conduct go-live. | 2024-06-16 | 2024-06-25 | Robert Taylor | 16 | 800 | Not Started
This table is designed for printing and export as an Excel-compatible format. All values are estimates and subject to change based on project updates.