## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget Allocation ($) | Resources Required
TS-001 | Project Planning & Kickoff | Jane Smith | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | 5,000 | Project Manager, Team Lead
TS-002 | Requirements Gathering | Mark Johnson | 2024-03-16 | 2024-04-05 | 20 | Medium | Not Started | 8,000 | Business Analyst, Stakeholders
TS-003 | Design Phase Completion | Lisa Chen | 2024-04-06 | 2024-05-10 | 35 | High | Planned | 15,000 | UI/UX Designer, Dev Team
TS-004 | Development & Testing | David Park | 2024-05-11 | 2024-07-30 | 90 | Critical | Not Started | 40,000 | Software Developers, QA Team
TS-005 | Deployment & Go-Live | Sarah Williams | 2024-08-01 | 2024-08-15 | 15 | High | Not Started | 7,500 | DevOps, Operations Team