## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget Allocation ($) | Actual Spend ($)
T001 | Project Kickoff Meeting | John Smith | 2024-03-01 | 2024-03-01 | 1 | High | Completed | 500 | 495
T002 | Requirements Gathering | Sarah Lee | 2024-03-05 | 2024-03-15 | 11 | Medium | In Progress | 2,500.00 | 1,800.00
T003 | Design Phase Finalization | David Chen | 2024-03-18 | 2024-04-05 | 18 | High | Planned | 6,000.00 | 0
T004 | Development Phase | Lisa Wang | 2024-04-08 | 2024-05-31 | 65 | Critical | Not Started | 15,000.00 | 0
T005 | Testing & QA Review | Mike Brown | 2024-06-10 | 2024-06-30 | 21 | High | Scheduled | 4,200.00 | 0
Summary |  |  |  |  | Total Budget: $28,200.00 | Total Actual Spend: $7,095.00