## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget (USD) | Actual Cost (USD)
T-001 | Product Research & Analysis | Alex Morgan | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | 5,000 | 3,200
T-002 | UI/UX Design Sprint | Jordan Lee | 2024-03-16 | 2024-04-05 | 21 | High | Not Started | 8,000 | 0
T-003 | Backend Development Phase 1 | Sam Patel | 2024-04-06 | 2024-05-10 | 35 | Medium | Planned | 12,000 | 0
T-004 | Mobile App Testing | Taylor Wong | 2024-05-11 | 2024-05-30 | 29 | Medium | Not Started | 4,500 | 0
T-005 | Market Launch Strategy | Mia Chen | 2024-06-01 | 2024-06-30 | 30 | High | Scheduled | 7,500 | 0
Total Budget (USD) | [8 empty] | 47,000
Total Actual Cost (USD) | [8 empty] | 6,100