## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Budget (USD) | Actual Spend (USD)
T001 | Project Kickoff Meeting | John Doe | 2024-03-15 | 2024-03-15 | 1 | High | Completed | 500 | 480
T002 | Requirement Gathering | Jane Smith | 2024-03-16 | 2024-03-25 | 10 | Medium | In Progress | 2,500.00 | 1,800.00
T003 | Design Phase | Alex Johnson | 2024-03-26 | 2024-04-10 | 15 | High | Planned | 6,000.00 | 0
T004 | Development Phase | Sam Lee | 2024-04-11 | 2024-05-31 | 51 | Critical | Not Started | 20,000.00 | 0