## Worksheet
Task | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Resources Required
Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-01 | 1 | High | Completed | Team Lead, Meeting Room, Zoom Access
Market Research Analysis | Research Analyst | 2024-04-02 | 2024-04-10 | 9 | Medium | In Progress | Research Analyst, Data Tools, Budget $1,500
UI/UX Design Phase | Design Team | 2024-04-11 | 2024-05-15 | 35 | High | Not Started | Design Team, Design Software, Access to Client Feedback
Development Sprint 1 | Engineering Team | 2024-05-16 | 2024-06-15 | 30 | High | Planned | Engineering Team, Servers, CI/CD Pipeline Access
Quality Assurance Testing | QA Team | 2024-06-16 | 2024-07-10 | 35 | Medium | Not Started | QA Team, Test Environment, Bug Tracking Tool