## Worksheet
Task ID | Task Description | Owner | Start Date | End Date | Priority Level | Status | Dependencies | Resource Allocation | Notes
T-001 | Conduct market research for new product launch | Anna Martinez | 2024-04-01 | 2024-04-15 | High | In Progress | None | Marketing Team (3 FTEs) | Include competitor analysis and customer survey data.
T-002 | Finalize product design mockups | James Lee | 2024-04-05 | 2024-04-25 | High | Planned | T-001 (completion) | Design Team (2 FTEs) | Ensure alignment with UX guidelines.
T-003 | Develop development plan and sprint timeline | Sarah Kim | 2024-04-10 | 2024-05-10 | Medium | Not Started | T-002 (completion) | Engineering Team (5 FTEs) | Break down into 4-week sprints.
T-004 | Conduct QA testing and bug resolution | David Chen | 2024-05-15 | 2024-06-15 | High | Not Started | T-003 (completion) | QA Team (2 FTEs) | Include regression and performance testing.
T-005 | Prepare launch campaign and promotional materials | Linda Ortiz | 2024-06-10 | 2024-06-30 | High | Planned | T-004 (completion) | Marketing Team (3 FTEs) | Include social media, email, and print elements.