## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependencies | Resource Required
TSK-001 | Market Research Phase | Jane Smith | 2024-04-01 | 2024-04-15 | High | In Progress | None | Research Team, Analytics Tools
TSK-002 | Product Design Finalization | Mike Johnson | 2024-04-16 | 2024-05-10 | Medium | Pending | TSK-001 | Design Team, UX Tools
TSK-003 | Development Sprint 1 | Sarah Lee | 2024-05-11 | 2024-06-05 | High | Not Started | TSK-002 | Engineering Team, Code Repository
TSK-004 | Quality Assurance Testing | David Kim | 2024-06-06 | 2024-06-25 | Medium | Planned | TSK-003 | QA Team, Test Automation Tools
TSK-005 | Launch Preparation Meeting | Emma Watson | 2024-07-01 | 2024-07-15 | Low | Not Started | TSK-004 | Project Manager, Marketing Team