## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Priority | Status | Progress (%) | Resource Required
TSK-001 | Market Research Phase | Jane Doe | 2024-03-15 | 2024-03-31 | High | Pending | 0% | Marketing Team
TSK-002 | Product Design Finalization | John Smith | 2024-03-20 | 2024-04-10 | High | In Progress | 65% | Design Team
TSK-003 | Development Sprint 1 | Alex Turner | 2024-04-01 | 2024-04-15 | Medium | Planned | 0% | Engineering Team
TSK-004 | User Testing & Feedback | Sara Kim | 2024-04-16 | 2024-05-01 | High | Scheduled | 0% | QA & UX Team
TSK-005 | Launch Preparation | Mike Brown | 2024-05-01 | 2024-05-15 | Critical | In Progress | 40% | Operations & Marketing