## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Priority Level | Status | Dependencies | Resources Required
T-001 | Market Research Analysis | Alex Turner | 2024-03-15 | 2024-03-25 | High | In Progress | None | Market data, analyst team
T-002 | Product Prototype Development | Samira Patel | 2024-03-26 | 2024-04-10 | Critical | Planned | T-001 completed | Engineering team, design tools
T-003 | User Testing & Feedback Collection | Jordan Lee | 2024-04-11 | 2024-04-20 | Medium | Not Started | T-002 completed | Beta testers, QA team
T-004 | Marketing Campaign Launch | Taylor Reed | 2024-04-21 | 2024-05-05 | High | Scheduled | T-003 completed | Marketing team, digital platforms