## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation
T-001 | Conduct market research for new product line | Sarah Johnson | 2024-03-05 | 2024-03-20 | 16 | High | In Progress | None | Marketing Team, Research Budget $5,000
T-002 | Develop Q3 campaign strategy | Mark Thompson | 2024-03-10 | 2024-03-31 | 32 | High | Planned | T-001 completed | Creative Team, Budget $8,000
T-003 | Finalize vendor contracts | Linda Chen | 2024-03-15 | 2024-03-25 | 11 | Medium | Not Started | T-002 approval required | Legal & Procurement, Budget $3,500
T-004 | Organize product launch event | David Ruiz | 2024-04-01 | 2024-04-05 | 5 | High | Pending Approval | T-003 completed, T-002 finalized | Event Management Team, Venue & Logistics
T-005 | Post-event customer feedback analysis | Emma Wilson | 2024-04-10 | 2024-04-15 | 6 | Low | Planned | T-004 completed | Analytics Team, Tools: SurveyMonkey, Excel