## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Progress (%) | Dependencies
TSK-001 | Market Research Analysis | Emma Wilson | 2024-03-15 | 2024-03-30 | High | In Progress | 65% | None
TSK-002 | Develop Product Prototype | David Chen | 2024-03-20 | 2024-04-10 | High | Not Started | 0% | TSK-001
TSK-003 | User Feedback Collection | Sophia Patel | 2024-04-01 | 2024-04-15 | Medium | Scheduled | 0% | TSK-002
TSK-004 | Final Product Testing | James Reed | 2024-04-20 | 2024-05-05 | High | Not Started | 0% | TSK-003
TSK-005 | Prepare Launch Presentation | Linda Foster | 2024-05-10 | 2024-05-15 | Medium | Not Started | 0% | TSK-004