## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Budget (USD) | Allocated Resources | Progress (%)
T-001 | Market Research Phase | Alex Morgan | 2024-03-15 | 2024-03-30 | 15 | On Track | 15,000 | 2 Analysts, 1 Researcher | 85%
T-002 | <Product Design Finalization | Jordan Lee | 2024-04-01 | 2024-04-18 | 18 | In Progress | 25,000 | 3 Designers, 1 UX Lead | 60%
T-003 | Development Sprint 1 | Samira Patel | 2024-04-20 | 2024-05-10 | 21 | Planned | 75,000 | 8 Developers, 2 QA Engineers | 0%
T-004 | QA Testing & Validation | Marcus Reed | 2024-05-15 | 2024-06-05 | 21 | Pending Approval | 30,000 | 4 Testers, 1 Lead QA | 25%
T-005 | Launch & Marketing Campaign | Taylor Boone | 2024-06-10 | 2024-06-30 | 21 | Not Started | 50,000 | Marketing Team (7) | 0%