## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Start Date | Duration (Days) | Resource Allocation | Dependencies
TSK-001 | Market Research Analysis | Sarah Johnson | 2024-04-15 | High | In Progress | 2024-03-25 | 15 | Marketing Team, 3 FTEs | None
TSK-002 | Product Prototype Design | David Chen | 2024-05-10 | Medium | Planned | 2024-04-05 | 30 | Design & Engineering, 2 FTEs | TKS-001
TSK-003 | Budget Finalization & Approval | Lisa Patel | 2024-05-30 | Low | Not Started | - | 5 | Finance Department, 1 FTE | TKS-002
TSK-004 | QA Testing & Bug Resolution | Marcus Reed | 2024-06-15 | High | Not Started | 2024-05-15 | 10 | QA Team, 4 FTEs | TKS-002, TSK-003
TSK-005 | Go-Live Deployment Plan | Elena Torres | 2024-07-10 | Medium | Not Started | 2024-06-01 | 7 | IT Operations, 3 FTEs | TKS-004