## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Progress (%)
T001 | Market Research Survey Design | Sarah Johnson | 2024-03-15 | 2024-03-25 | On Track | High | None | 85%
T002 | Competitor Analysis Report | Michael Chen | 2024-03-18 | 2024-04-05 | In Progress | Medium | T001 | 60%
T003 | Product Roadmap Drafting | Lisa Wong | 2024-04-01 | 2024-04-15 | Pending Approval | High | T002 | 30%
T004 | User Feedback Workshop | David Park | 2024-04-10 | 2024-04-13 | Scheduled | Medium | T003 | 0%
T005 | Final Product Launch Plan | Emma Reed | 2024-04-20 | 2024-05-10 | Not Started | High | T003, T004 | 0%