## Worksheet
Task | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status
Market Research & Analysis | Sarah Chen | 2024-03-01 | 2024-03-15 | 15 | High | On Track
Product Design Finalization | David Kim | 2024-03-05 | 2024-03-25 | 21 | High | In Progress
Development Phase (Beta) | Team A | 2024-03-10 | 2024-04-10 | 41 | Critical | Scheduled
User Testing & Feedback | Linda Wu | 2024-04-15 | 2024-04-30 | 16 | Medium | Not Started
Final Review & Launch Prep | Project Manager | 2024-05-05 | 2024-05-15 | 11 | High | Planned