## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Priority | Status | Notes
T001 | Market Research Analysis | Alex Morgan | 2024-03-15 | 2024-03-25 | High | In Progress | Gather competitor data and customer feedback.
T002 | Product Roadmap Draft | Jordan Lee | 2024-03-18 | 2024-04-05 | Medium | Planned | Finalize features and timeline for Q2.
T003 | Team Training Session | Taylor Reed | 2024-03-22 | 2024-03-23 | Low | Scheduled | Introduce new CRM tools to the sales team.
T004 | Quarterly Financial Review | Samira Patel | 2024-03-30 | 2024-04-01 | High | Pending | Review expenses and revenue projections.
T005 | Client Feedback Survey | Morgan Hall | 2024-04-01 | 2024-04-10 | Medium | Not Started | Distribute survey to 50 active clients.