## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T001 | Market Research & Analysis | Sarah Lee | 2024-03-15 | 2024-03-25 | 11 | High | In Progress | None | Gather customer insights from primary and secondary sources.
T002 | Product Roadmap Development | James Chen | 2024-03-26 | 2024-04-10 | 15 | High | Planned | T001 | Align with market research findings and stakeholder feedback.
T003 | UI/UX Design Phase | Lena Patel | 2024-04-11 | 2024-05-05 | 25 | Medium | Scheduled | T002 | Create wireframes and prototypes based on product roadmap.
T004 | Development Sprint 1 | Mike Torres | 2024-05-06 | 2024-05-31 | 26 | High | Not Started | T003 | Build core functionality using agile methodology.
T005 | QA Testing & Bug Resolution | Anna Kim | 2024-06-01 | 2024-06-15 | 15 | High | Planned | T004 | Conduct full system testing and fix critical bugs.