## Worksheet
Task | Owner | Due Date | Priority | Status | Notes
Product Vision Workshop | Emma Chen | 2024-03-15 | Highest | Not Started | Cross-functional alignment with engineering and design teams.
Market Research Analysis | Liam Torres | 2024-03-25 | High | In Progress | Data collection from 3 key competitors.
Prototype Development (MVP) | Sarah Kim | 2024-04-10 | High | Not Started | Focused on core user flows and feedback loop.
First Beta User Testing | James Reed | 2024-04-20 | Middle | Planned | Target 15 early adopters for usability feedback.
Go-to-Market Strategy Draft | Ava Patel | 2024-05-05 | High | Not Started | Incorporate pricing and channel recommendations.
Team Onboarding Plan | Director of Operations | 2024-03-30 | Low | Completed | All new hires have completed training modules.