## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Priority | Status | Dependence | Assigned To | Estimated Hours | Actual Hours | Notes
TSK-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-05 | High | Completed | None | Project Manager | 4 | 4 | Initial project alignment and team briefing.
TSK-002 | Requirement Gathering | John Smith | 2024-04-06 | 2024-04-15 | High | In Progress | TSK-001 | Team A | 20 | 8 | Client interviews scheduled and documentation in progress.
TSK-003 | Design Phase Review | Sarah Lee | 2024-04-16 | 2024-04-20 | Medium | Pending | TSK-002 | Design Team | 15 | 0 | Waiting for client feedback on wireframes.
TSK-004 | Development Start | Mike Johnson | 2024-04-21 | 2024-05-10 | High | Not Started | TSK-003 | Engineering Team | 60 | 0 | Frontend and backend development to begin.
TSK-005 | QA Testing Phase | Lisa Wang | 2024-05-11 | 2024-05-25 | Medium | Not Started | TSK-004 | QA Team | 40 | 0 | End-to-end testing and bug reporting to begin.