## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Notes
T001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 | High | Scheduled | None | Finalize project scope and objectives.
T002 | Requirements Gathering | Mark Johnson | 2024-04-02 | 2024-04-10 | High | In Progress | T001 | Collect input from stakeholders.
T003 | Design Phase | Lisa Chen | 2024-04-11 | 2024-04-25 | Medium | Planned | T002 | Create wireframes and UI mockups.
T004 | Development Start | Alex Rivera | 2024-04-26 | 2024-05-15 | High | Not Started | T003 | Begin coding based on design.
T005 | Testing & QA | Sarah Kim | 2024-05-16 | 2024-05-31 | High | Planned | T004 | Conduct unit and integration testing.
T006 | Deployment | David Wong | 2024-06-01 | 2024-06-01 | Critical | Scheduled | T005 | Launch to production environment.