## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Progress (%) | Next Action
T001 | Project Kickoff Meeting | Sarah Johnson | 2024-04-15 | High | Completed | 2024-04-10 | 100% | Review documentation
T002 | Market Research Analysis | Michael Lee | 2024-05-10 | Medium | In Progress | 2024-04-12 | 65% | Submit draft report by Friday
T003 | UI/UX Design Finalization | Emma Chen | 2024-05-25 | High | Pending | 2024-04-18 | 30% | Present design mockups to team
T004 | Development Sprint Planning | David Kim | 2024-06-10 | High | Not Started |  | 0% | Finalize sprint scope by April 28
T005 | QA Testing Phase | Linda Patel | 2024-07-05 | Medium | Scheduled | 2024-06-15 | 15% | Complete initial test cases