## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Notes
TSK-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | High | Completed | None | Initial planning session with stakeholders.
TSK-002 | Market Research Survey | Jane Smith | 2024-04-03 | 2024-04-10 | Medium | In Progress | TSK-001 | Collect feedback from 500 customers.
TSK-003 | Design Phase Finalization | Alex Chen | 2024-04-11 | 2024-04-25 | High | Not Started | TSK-002 | Finalize UI/UX mockups based on survey data.
TSK-004 | Development Setup | Mike Brown | 2024-04-26 | 2024-05-05 | Medium | Not Started | TSK-003 | Configure development environment and tools.
TSK-005 | Testing & Quality Assurance | Sarah Lee | 2024-05-06 | 2024-05-20 | High | Not Started | TSK-004 | Conduct unit and integration testing.