## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority Level | Status | Dependence On | Resource Required | Notes
TSK-001 | Project Kickoff Meeting | John Smith | 2024-03-05 | 2024-03-05 | 0 | High | Completed | None | Facilitator, Meeting Room | Initial project alignment and goals setting.
TSK-002 | Requirement Gathering | Lisa Chen | 2024-03-06 | 2024-03-15 | 10 | Medium | In Progress | TSK-001 | Stakeholder interviews, Documentation | Finalize user requirements and send to review.
TSK-003 | Design Phase Initiation | Mike Torres | 2024-03-16 | 2024-03-30 | 25 | High | Not Started | TSK-002 | UI/UX Designer, Design Tools | Create wireframes and mockups based on requirements.
TSK-004 | Development Start | Sarah Kim | 2024-04-01 | 2024-05-30 | 60 | Critical | Not Started | TSK-003 | Backend & Frontend Developers, Server Setup | Begin coding and integration with design.
TSK-005 | Testing & QA Review | David Lee | 2024-06-01 | 2024-06-15 | 15 | High | Not Started | TSK-004 | QA Team, Test Environment | Conduct functional and regression testing.
TSK-006 | Final Approval & Deployment | Emma Rodriguez | 2024-06-16 | 2024-06-18 | 3 | High | Not Started | TSK-005 | Operations Team, Production Server | Deploy system to production and notify stakeholders.