## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependence ID | Resource Required | Notes
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | Planned | - | Project Manager, Room A | Finalize project scope and objectives.
TSK-002 | Requirement Gathering | Alex Johnson | 2024-04-04 | 2024-04-15 | High | In Progress | TSK-001 | Business Analyst, Stakeholders | Collect input from key departments.
TSK-003 | Design Phase Completion | Maria Chen | 2024-04-16 | 2024-04-30 | Medium | Not Started | TSK-002 | UI/UX Designer, Design Tools | Finalize wireframes and user flows.
TSK-004 | Development Start | David Lee | 2024-05-01 | 2024-05-31 | High | Planned | TSK-003 | Development Team, Servers | Begin coding based on approved designs.
TSK-005 | Testing & QA Review | Sophia Kim | 2024-06-01 | 2024-06-15 | High | Not Started | TSK-004 | QA Team, Test Environment | Conduct unit and integration testing.