## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Priority th> | Status | Budget (USD) | Resource Allocation
TSK-001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-03 | High | In Progress | 5,000.00 | 1 Full-Time
TSK-002 | Market Research & Analysis | Sarah Lee | 2024-04-05 | 2024-04-18 | Medium | Planned | 8,500.00 | 2 Analysts
TSK-003 | UI/UX Design Phase | Mike Chen | 2024-04-20 | 2024-05-15 | High | Not Started | 15,000.00 | 3 Designers
TSK-004 | Backend Development | David Kim | 2024-05-16 | 2024-07-31 | Critical | Not Started | 45,000.00 | 6 Developers
TSK-005 | QA Testing & Deployment | Linda Wong | 2024-08-01 | 2024-08-31 | Medium | Planned | 12,000.00 | 4 QA Engineers