## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-03 | High | In Progress | Confirm all stakeholders present.
T002 | Market Research Analysis | Sarah Chen | 2024-04-05 | 2024-04-15 | Medium | Pending | Data collection phase complete.
T003 | Product Design Finalization | David Lee | 2024-04-10 | 2024-04-25 | High | Not Started | Design review with legal team required.
T004 | Development Sprint Planning | Emma Rodriguez | 2024-04-18 | 2024-04-30 | Medium | Scheduled | Review sprint goals with engineering lead.
T005 | QA Testing Phase | James Wilson | 2024-05-01 | 2024-05-10 | High | Not Started | All modules must be tested in sequence.