## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
TSK-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | High | Completed | Initial project planning session.
TSK-002 | Requirements Gathering | John Smith | <+ td>2024-04-022024-04-15 | Middle | In Progress | Collecting input from stakeholders.
TSK-003 | Design Phase Review | Sarah Lee | 2024-04-16 | 2024-04-25 | High | Pending Approval | Final design draft to be reviewed by PM.
TSK-004 | Development Setup | Mike Chen | 2024-04-26 | 2024-05-10 | Middle | Not Started | Configure development environment.
TSK-005 | QA Testing Phase | Lisa Wong | 2024-05-11 | 2024-05-31 | High | Scheduled | Beta testing to be conducted.
Page 1 of Multi-Page Task Scheduling Report