## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-01 | High | Completed | Finalize project scope and timeline.
T002 | Design Phase Review | Sarah Lee | 2024-04-05 | 2024-04-10 | Medium | In Progress | Review wireframes and user feedback.
T003 | Development Phase Start | Mike Chen | 2024-04-11 | 2024-05-15 | High | Pending | Begin backend integration.
T004 | QA Testing | Linda Wang | 2024-05-16 | 2024-05-30 | Medium | Not Started | Validate functionality across devices.
T005 | Final Deployment | David Park | 2024-06-01 | 2024-06-03 | High | Planned | Roll out to production environment.