## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | 1 | High | Completed | Initial planning session for Q2 goals.
T002 | Design Phase Review | Sarah Lee | 2024-03-18 | 2024-03-25 | 7 | Medium | In Progress | Review final wireframes with stakeholders.
T003 | Development Sprint | Mike Johnson | 2024-03-26 | 2024-04-10 | 15 | High | Planned | Implement core functionality.
T004 | Quality Assurance Testing | Lisa Wong | 2024-04-11 | 2024-04-18 | 7 | Medium | Pending | Run automated and manual tests.
T005 | Go-Live Deployment | David Brown | 2024-04-19 | 2024-04-19 | 1 | High | Scheduled | Deploy to production environment.