## Worksheet
Quarter | Task Category | Task Description | Assigned To | Due Date | Priority Level | Status
Q1 (Jan–Mar) | Project Planning | Finalize project scope and deliverables | John Doe | 2024-03-15 | High | In Progress
Q1 (Jan–Mar) | Resource Allocation | Assign team members to core tasks | <Sarah Lee | 2024-02-28 | Medium | Completed
Q1 (Jan–Mar) | Market Research | Conduct competitor analysis and customer feedback surveysMaria Garcia | 2024-04-10 | High | Pending
Q2 (Apr–Jun) | Development Phase | Build MVP and conduct internal testing | David Kim | 2024-06-30 | High | Not Started
Q2 (Apr–Jun) | Stakeholder Review | Present progress to executive team | Lisa Chen | 2024-05-15 | Medium | Planned
Q3 (Jul–Sep) | Go-Live Preparation | Finalize launch plan and training materials | James White | 2024-09-01 | High | Not Started
Q4 (Oct–Dec) | Performance Review | Analyze KPIs and prepare annual report | Emma Patel | 2024-12-15 | Medium | <Planned