## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependencies
T001 | Project Kickoff Meeting | John Smith | 2024-04-01 | 2024-04-03 | High | Planned | None
T002 | Market Research Analysis | Sarah Lee | 2024-04-05 | 2024-04-15 | Medium | In Progress | T001
T003 | Design Wireframes | Mike Chen | 2024-04-16 | 2024-04-25 | High | Pending | T002
T004 | Development Phase Launch | Lisa Wong | 2024-05-01 | 2024-05-31 | Critical | Not Started | T003, T005
T005 | Testing & Quality Assurance | David Park | 2024-06-01 | 2024-06-15 | High | Planned | T004