## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Estimated Duration (Days) | Dependencies | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | Completed | Low | 1 |  | Initial planning session.
T002 | Market Research Phase | Sarah Lee | 2024-03-16 | 2024-03-31 | In Progress | Medium | 16 | T001 | Gather customer insights and trends.
T003 | UI/UX Design Finalization | Mike Chen | 2024-04-01 | 2024-04-15 | Not Started | High | 15 | T002, T004 | Finalize wireframes and design mockups.
T004 | Backend Development Start | Alex Rivera | 2024-04-16 | 2024-05-31 | Not Started | High | 47 | T003 | Begin server setup and API integration.
T005 | QA Testing Phase | Lisa Wang | 2024-06-01 | 2024-06-30 | Not Started | Medium | 30 | T004 | Conduct end-to-end functional testing.