## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Priority | Status | Estimated Hours | Progress (%) | Notes
TSK-001 | Project Planning Meeting | Jane Doe | 2024-04-01 | 2024-04-03 | High | In Progress | 4 | 60% | Review project scope and timeline.
TSK-002 | Design UI Mockups | John Smith | 2024-04-05 | 2024-04-15 | Medium | Not Started | 8 | 0% | Create wireframes for all screens.
TSK-003 | Develop Backend API | Alex Turner | 2024-04-10 | 2024-05-10 | High | In Progress | 20 | 45% | Integrate authentication and database.
TSK-004 | User Testing Session | Team Lead | 2024-05-15 | 2024-05-18 | Medium | Not Started | 6 | 0% | Gather feedback from beta users.