## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%) | Notes
TSK-001 | Project Initiation Meeting | John Doe | 2024-04-01 | 2024-04-03 | Completed | Medium | 100% | All stakeholders confirmed.
TSK-002 | Requirements Gathering | Jane Smith | 2024-04-04 | 2024-04-15 | In Progress | High | 65% | Waiting on client feedback.
TSK-003 | UI/UX Design Phase | Alex Turner | 2024-04-16 | 2024-05-10 | Planned | Medium | 0% | Design assets to be reviewed by PM.
TSK-004 | Development Sprint 1 | Sam Lee | 2024-05-11 | 2024-05-31 | Pending Approval | High | 20% | Needs review from QA team.