## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Responsible Person | Priority Level | Status | Estimated Duration (Days) | Budget Allocation ($)
T001 | Market Research Phase | 2024-03-15 | 2024-03-31 | Sarah Johnson | High | In Progress | 16 | $5,000
T002 | <Product Design Finalization | 2024-04-01 | 2024-04-15 | Mike Chen | High | Pending Approval | 15 | $8,000
T003 | Development Testing Phase | 2024-04-16 | 2024-05-10 | Lisa Wong | Medium | Not Started | 25 | $12,000
T004 | Client Presentation & Review | 2024-05-11 | 2024-05-18 | David Kim | High | <Scheduled | 7 | $3,500