## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Estimated Duration (Days) | Budget Allocation ($) | Actual Cost ($)
T-001 | Market Research Phase | 2024-03-15 | 2024-03-31 | Alice Johnson | High | In Progress | 16 | 5,000.00 | 4,200.00
T-002 | Product Design Finalization | 2024-04-01 | 2024-04-15 | Bob Smith | High | Not Started | 15 | 8,000.00 | 0
T-003 | Development Sprint 1 | 2024-04-16 | 2024-05-10 | Charlie Lee | Critical | On Track | 35 | 20,000.00 | 18,500.00
T-004 | QA Testing & Validation | 2024-05-11 | 2024-05-31 | Diana Patel | Medium | Scheduled | 20 | 6,500.00 | 6,350.00
T-005 | User Training Program | 2024-06-01 | 2024-06-15 | Eve Morgan | Low | Not Started | 15 | 3,000.00 | 0
Summary Metrics |  |  |  |  | Total Budget Allocated: $32,500.00 ¦ Total Actual Cost: $39,150.00