## Worksheet
Date | Task Description | Assigned To | Start Time | End Time | Duration (hrs) | Priority | Status | Resources Required | Budget Allocation ($) | Actual Cost ($) | Variance ($) | Notes
2024-04-01 | Project Kickoff Meeting | John Smith | 09:00 AM | 10:30 AM | 1.5 | High | Completed | Team Lead, Room 101 | 500 | 480 | 20 | All stakeholders present and aligned.
2024-04-05 | Design Phase Planning | Sarah Lee | 10:00 AM | 12:30 PM | 2.5 | Medium | In Progress | Design Team, Sketching Tools | 800 | 650 | 150 | Final wireframes pending approval.
2024-04-12 | Development Sprint 1 | Michael Brown | 08:30 AM | 05:00 PM | 8.5 | High | Completed | Backend Team, Servers, API Keys | 3,200.00 | 3,150.00 | 50 | All modules integrated successfully.
2024-04-18 | User Testing Session | Lisa Wong | 11:00 AM | 02:00 PM | 3 | High | Completed | 5 Test Participants, QA Tools | 1,200.00 | 1,180.00 | 20 | Minor usability issues identified.
2024-04-25 | Final Documentation | David Kim | 09:30 AM | 12:30 PM | 3 | Low | Pending Review | Content Writer, Templates | 400 | - | - | Awaiting sign-off from Product Manager.