## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Progress (%)
TS-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | Completed | High | 8 | 8 | 100%
TS-002 | <+Design Phase PlanningAlex Johnson | 2024-04-05 | 2024-04-15 | In Progress | Medium | 20 | 12 | 60%
TS-003 | Client Requirements Review | Sarah Lee | 2024-04-10 | 2024-04-18 | Pending | High | 15 | 0 | 0%
TS-004 | Development Environment Setup | Michael Brown | 2024-04-19 | 2024-04-25 | Not Started | Low | 10 | 0 | 0%