## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Estimated Duration (Days) | Allocated Budget | Actual Cost (USD) | Progress (%) | Notes
TS-001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | John Doe | High | Completed | 1 | 200 | 195.5 | 100 | All stakeholders present and objectives agreed.
TS-002 | Market Research Phase | 2024-04-03 | 2024-04-15 | Jane Smith | Medium | In Progress | 13 | $3,500.00 | $2,875.00 | 75 | Surveys distributed to 1,200 users; data analysis pending.
TS-003 | UI/UX Design Finalization | 2024-04-16 | 2024-05-05 | Alex Rivera | High | Planned | 20 | $8,000.00 | - | 0 | Design mockups approved by stakeholders.
TS-004 | Backend Development Start | 2024-05-06 | 2024-06-30 | Sam Kim | High | Not Started | 65 | $15,000.00 | - | 0 | Technical requirements finalized.
TS-005 | QA Testing & Bug Fixing | 2024-07-01 | 2024-07-31 | Linda Chen | Medium | Planned | 30 | $6,000.00 | - | 0 | Test plan under review.